## Burndown Chart
Sprint 4 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4
1 | Conception of use Cases and their Descriptions | 4 | 2 | 1 | 1 | 0
2 | Reviews of use Cases and their Descriptions | 3 | 1 | 1 | 1 | 0
3 | Development of backend for the previously idealized new features | 4 | 2 | 2 | 0 | 0
4 | Development of fronted for the previously idealized new features | 15 | 0 | 0 | 5 | 10
Completed Effort |  | 0 | 5 | 4 | 7 | 10
Remaining Effort |  | 26 | 21 | 17 | 10 | 0
Ideal Burndown |  | 26 | 23.6364 | 21.2727 | 18.9091 | 16.5455
5