## Burndown Chart
Sprint 5 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-12-02 | 2022-12-03 | 2022-12-04
|  | Day 0 | Day 1 | Day 2 | Day 3
1 | Finish Conception of use Cases and their Descriptions | 1 | 1 | 0 | 0
2 | Finish Reviews of use Cases and their Descriptions | 1 | 0 | 0 | 1
3 | Finish Junit tests for backend | 1 | 0 | 1 | 0
4 | Fixing and adapting the backend according to the frontend recently found needs | 4 | 1 | 2 | 1
5 | Continue and finish development of fronted for the previously idealized features | 30 | 12 | 12 | 6
6 | Code base metrics analysis | 16 | 0 | 3 | 13
7 | Code base metrics reviews | 5 | 0 | 0 | 5
8 | Project report | 20 | 2 | 0 | 18
9 | Video | 8 | 0 | 0 | 8
Completed Effort |  | 0 | 16 | 18 | 52
Remaining Effort |  | 86 | 70 | 52 | 0
Ideal Burndown |  | 86 | 78.1818 | 70.3636 | 62.5455
5