## Burndown Chart
Backlog | TODO |  | In progress |  | Reviewing | Done
Identify Code Smells | Identify 3 Code Smells By: Gonçalo Rodrigues | -> | Identify 3 Code Smells By: Gonçalo Rodrigues | -> | Identify 3 Code Smells By: Gonçalo Rodrigues Reviewers: Joana Cruz, Bárbara Correia. Gonçalo Gomes
| Identify 3 Code Smells By: Gonçalo Gomes | -> | Identify 3 Code Smells By: Gonçalo Gomes
| Identify 3 Code Smells By: Guilherme Santana | -> | Identify 3 Code Smells By: Guilherme Santana | -> | Identify 3 Code Smells By: Guilherme Santana Reviewers: Bárbara Correia, Gonçalo Gomes, Gonçalo Rodrigues
| Identify 3 Code Smells By: Bárbara Correia | -> | Identify 3 Code Smells By: Bárbara Correia | -> | Identify 3 Code Smells By: Bárbara Correia Reviewers: Gonçalo Rodrigues, Guilherme Santana, Joana Cruz
| Identify 3 Code Smells By: Joana Cruz | -> | Identify 3 Code Smells i By: Joana Cruz | -> | Identify 3 Code Smells By: Joana Cruz Reviewers: Guilerme Santana, Gonçalo Rodrigues, Gonçalo Gomes
Identify Design Patterns | Identify 3 Pattern Designs By: Gonçalo Rodrigues | -> | Identify 3 Pattern Designs By: Gonçalo Rodrigues | -> | Identify 3 Pattern Designs By: Gonçalo Rodrigues Reviewers: Joana Cruz, Bárbara Correia. Gonçalo Gomes
| Identify 3 Pattern Designs By: Gonçalo Gomes | -> | Identify 3 Pattern Designs By: Gonçalo Gomes
| Identify 3 Pattern Designs By: Guilherme Santana | -> | Identify 3 Pattern Designs By: Guilherme Santana
| Identify 3 Pattern Designs By: Bárbara Correia | -> | Identify 3 Pattern Designs By: Bárbara Correia
| Identify 3 Pattern Designs By: Joana Cruz | -> | Identify 3 Pattern Designs By: Joana Cruz | -> | Identify 3 Pattern Designs By: Joana Cruz Reviewers: Guilerme Santana, Gonçalo Rodrigues, Gonçalo Gomes